# The projects page and the project dashboard

Picking an office now opens that office's projects, and each project opens its dashboard: every variation on the job with its value and status, and totals of what is approved and what is still pending.

Offices  ›  VIC  ›  Austin Hospital 1507V

[ Variations 2 ] [ Total $3,410 ] [ Approved $1,600 ] [ Pending $0 ] …

VAR-001     RPZ Valve Relocation    $1,600.00   Approved   …   Open

VAR-001.1 RPZ Valve Relocation    $2,240.00   Draft      …   Open

VAR-002     Additional floor waste  $1,170.00   Draft      …   Open

Everything shown comes from the two flows the app already has: Get projects for the list, and the variation log for the variations. Three changes in SharePoint and Power Automate make it complete. The app works before any of them are made — they decide how much it can show and how fast.

| Change | Without it | With it |
| --- | --- | --- |
| 1 · Five new columns in the Variation Log list | Values, statuses, approvals and commentary still show — they are read from each row's saved form | They are real columns: visible, sortable and totalled in SharePoint and Excel |
| 2 · Map them in the log write flow (flow 5) | The columns stay empty | Every save, status change, approval and comment fills them |
| 3 · One expression in the log read flow (flow 4) | The projects page asks the log once per project | One call per office |

# How the statuses work

| Status | Set by |
| --- | --- |
| Draft | A variation saved to the log but never downloaded |
| Submitted | Automatically, the first time its PDF is downloaded |
| Approved | On the dashboard — the status list in the table, or the Builder commentary window |
| Rejected | The same |

## Approved value and date

Entered by hand in the Builder commentary window, from what the builder actually approved. They are not taken from the schedule of rates — the window shows the schedule's figure beside them for reference only. The dashboard's Approved total adds up the approved values entered, and says how many approved variations do not have one yet.

The approved value can also be entered as a percentage of the variation's value: type it in Approved %, or click 100%, 80%, 50% or 20%, and the value is worked out (80% of $1,600.00 is $1,280.00). Typing the value instead fills in the percentage. Only the value is saved, so no new column is needed; the dashboard shows the share under each approved value (90.63% of value).

## Builder commentary

Builder commentary on each row opens a window with the variation's thread: every entry timestamped when it is added, with who it is from (the builder's contact) and who entered it (your name, remembered on this computer, or the signed-in Microsoft account). Each entry is saved to the log as soon as it is added.

Edit and Delete sit on every entry. An edited entry keeps its original timestamp and shows edited with when and by whom. A deleted entry leaves the thread and the BuilderCommentary column, but is kept behind Show deleted with when and by whom it was deleted, so the record of what the builder said is never silently lost.

Two people can work on the same variation's commentary at once without losing each other's changes: the window reads the row again just before it saves and merges the two threads entry by entry, and where both changed the same entry the later change wins. A save from the form does the same. A revision has a thread of its own; the original's stays with the original.

A revision (VAR-001.1) is a new submission, so it starts again at Draft. Totals count each variation once, at its latest revision; earlier revisions are listed and marked Superseded.

Variations logged before this existed show as Submitted if their PDF was downloaded, otherwise Draft. Ones saved before the schedule of rates existed have no value and show — until they are reopened and saved again.

# 1 · Add five columns to the Variation Log list

In the list: + Add column, one at a time. Type the name exactly as shown — no spaces — so the internal name is clean; rename the display name afterwards if you like.

| Name | Type | Notes |
| --- | --- | --- |
| Status | Choice | Choices Draft, Submitted, Approved, Rejected, spelled exactly. Default Draft |
| ValueExGst | Currency (or Number, 2 decimals) |  |
| ApprovedValue | Currency (or Number, 2 decimals) |  |
| ApprovedDate | Date and time, Date only |  |
| BuilderCommentary | Multiple lines of text, plain text | The whole thread as readable text, newest last |

registers/Variation Log.xlsx lists them with the rest.

A log per state? Add them to every state's list.

# 2 · Map them in flow 5 (the log write)

The app already sends them. Open flow 5 and, in both the Update item (If yes) and the Create item (If no), fill the five new fields:

| Column | Value |
| --- | --- |
| Status Value | @{outputs('Incoming')?['status']} |
| ValueExGst | @{outputs('Incoming')?['valueExGst']} |
| ApprovedValue | @{outputs('Incoming')?['approvedValue']} |
| ApprovedDate | @{outputs('Incoming')?['approvedDate']} |
| BuilderCommentary | @{outputs('Incoming')?['builderCommentary']} |

Type each one in through the expression editor (fx) without the @{ } — e.g. outputs('Incoming')?['status'] — so it goes in as an expression, not text.

A Choice column shows as Status Value in the action. ApprovedValue and ApprovedDate arrive as null until a variation is approved, which clears the cell — that is what you want.

One thing flow 5 already does that matters more now. It sets DownloadedAt from whatever arrives, so a save that does not send it would blank it. The dashboard sends the row's existing DownloadedAt back with every status change, so changing a status never loses when it was issued.

# 3 · Let flow 4 (the log read) answer for a whole office

The projects page wants every variation in the office in one call, so it sends the office with no project: { "action": "listState", "state": "VIC", "projectId": "" }. Today's filter cannot take that — ProjectId eq  with nothing after it is not a valid query — so the app falls back to asking project by project, and says so under the totals.

One change fixes it. In flow 4's Get items, replace the Filter Query with this expression — through the expression editor (fx):

if(empty(outputs('Incoming')?['projectId']),

concat('State eq ''', outputs('Incoming')?['state'], ''''),

concat('State eq ''', outputs('Incoming')?['state'], ''' and ProjectId eq ', outputs('Incoming')?['projectId']))

(In an expression a single quote inside a string is written twice, hence the ''.) It reads: no project → State eq 'VIC'; a project → State eq 'VIC' and ProjectId eq 7, exactly as before. Nothing else about the flow changes, and every existing call behaves the same.

Then, still on Get items:

- Top Count 5000

- … → Settings → Pagination on, threshold 5000 — an office with years of variations can pass the 100-row page Get items stops at otherwise.

A log per state? The Switch you already have picks the list from state, which is still sent, so nothing else is needed.

## Checking it

Open an office in the app. The totals should appear without the line "Totals read project by project…" under them. In the flow's run history there is one run for the page rather than one per project.

# What the app sends now

Flow 5 receives five more fields with every write:

| Field | Example |
| --- | --- |
| status | Approved |
| valueExGst | 2440 (a number), or null when nothing is priced |
| approvedValue | 2440, or null |
| approvedDate | 2026-10-20, or null |
| builderCommentary | 20 Oct 2026, 09:15 am — Glen O'Connor, Kapitol (entered by Ben Smith): and the text, one entry after another |

Flow 4 additionally receives "action": "listState" with an empty projectId from the projects page. The variation log's row shape in its reply is unchanged.